## Slide 1: “Study and identification of a standard toolkits for wooden furniture making artisans”
Dr S P Mishra (PI)
Principal Scientific Officer (Rural Craft & Engg)
Mr Vinod Wankar (Co-PI)
Senior Scientific Officer (Rural Craft & Engg)
Mahatma Gandhi Institute for Rural Industrialization
Maganwadi, Wardha, 442001

## Slide 2: Drafting of, Guideline for Directorate of RENTI, KVIC
While serving at KVIC, I undertook the drafting of guidelines for the Directorate of RENTI, KVIC, Mumbai.
During that time, higher authorities recommended investigating toolkits for artisans specializing in wooden furniture-making.
Consequently, a video conference was organized in 2020-21, with participation from experts representing Visva Bharti, VNIT Nagpur, as well as various other organizations.
During the video-conference, it was collectively decided that a systematic study should be undertaken to identify the optimal set of power tools tailored for wooden furniture-making artisans.

## Slide 3: Status of Indian Wooden Furniture Making Artisans
During 2022-23, the Department of RC&E, MGIRI, Wardha has systematically studied the "Need for appropriate tools and machines for making wooden furniture.“
In this study, institutes specialized in wooden furniture designing and manufacturing, like the Institute of Wood Science and Technology, Bangalore, Bhartiya Skill Development University, Jaipur, ex-KVIC officials, NGOs working on the concerned field, artisans from different parts of the country and enterprises who are making wooden furniture participated, and following recommendations have been made –
Traditional artisans who make wooden furniture need systematic training in using power tools.
MGIRI could select the set of most appropriate power tools, and systematic training for using for appropriate benefits could be framed.
On an experimental basis, MGIRI will identify most appropriate power tools with the help of specialized institutes working on designing of wooden furniture.
MGIRI will identify a few artisans for conducting experiments on selection of most appropriate power tools for making of wooden furniture with the help of respective KVIC state offices.
Bhartiya Skill Development University, Jaipur, will provide all types of hand-holding support on a cost basis.

## Slide 4: Opportunities Evolving in Wooden Furniture Sector
Indian woodworking industry is one of the quickest-growing sectors contributing to the growth of India’s economy.
India has about 1,00,000 listed existing woodworking units, and overseas 2,00,000 artisans are employed in these industrial units.
Over 3,000 furniture business units in the prearranged sector have been industrialized in India and the numbers are cumulative every year.
According to a study by the World Bank, India’s organized furniture industry will keep growing at 20% annually. India positions at 14th position in the world furniture market. Also, it is one of the fastest-growing industries in India.
The India Furniture market size reached US$ 21.4 Billion in 2022. Looking forward, IMARC Group expects the market to reach US$ 41.4 Billion by 2028, exhibiting a growth rate (CAGR) of 11.6% during 2023-2028.
The different studies regarding carpentry artisans reported that despite the wide range of opportunities, artisans involved in making of furniture remain socially isolated because of the lack of upliftment of artisans.
Hand tools should be improved because the work efficiency of the crafts depends on tools.
The production process can be made easy using improved tools and advanced machines, providing and increasing extra leverage for artisans.
It also suggested that the carpentry artisans belonged to poor backgrounds with low education levels, which created a long distance between artisans and modern technology.

## Slide 5: Recommendation for Revival of Wooden Furniture Sector
  Hand tools should be improved because the work efficiency of the crafts depends on tools. The production process can be made easy using improved tools and advanced machines, which can provide and increase the extra leverage to the artisans.
  Designers' input can be added to improve the product line, which can open new doors for the wood carving craft to come out of its restricted technique of designing, which will develop a unique and contemporary look.
  Awareness programmes such as short-term courses, brainstorming workshops, seminars based on craft innovation, furniture designing, and design study should be organized by the Government of India to train the artisans to use new technology wherever possible in an attempt to make quality products using innovative opportunities.
  There should be training centers with diverse fields for the training of the artisans that would educate them about the basic training of computers, online trading, certification, and exposure to new initiatives and also the government's policies.
  Woodcraft education courses should be introduced in secondary schools and the Department of Arts and Design, which will connect the young generation with their culture, tradition, and heritage.

## Slide 6: Objectives of Proposed Study
    The main objectives of the project proposal are the following: -
      to identify the set of best power tools for furniture manufacturing artisans.
      to identify suitable furniture manufacturing master craftsman (two to three from selected zone of KVIC with the help of KVIC State Offices) for conducting the trial of selected power tools.
      to identify the difficulties after using the power tools for furniture manufacturing.
      to support with optimized programme on “furniture manufacturing” to the Directorate of RENTI, KVIC, Mumbai to serve and support on PAN India.
      to provide a new path to each stockholder of wooden furniture manufacturing sector.

## Slide 7: The availability of Proposed Technology/Intervention
The Bharatiya Skill Development University Jaipur is running 3 years of B. Voc in Woodworking Skills and two years in M. Voc in Woodworking Skills on Swiss based dual education model.
The Bharatiya Skill Development University Jaipur is ready to conduct experiment on -
two-month experimentation for selection of power tools for artisans for creation of better designs of wooden furniture and
six months experimentation for “Designing and making of furniture” for engineering graduates who can support the master craftsman and start their own businesses.
Around two to three artisans (Matric pass) from selected zone (as per availability of fund) will be selected for conducting the experiment and they will participate in two-months experimentation at Jaipur.
In next stage few interested Engineering graduates may be selected from particulare zone to support the artisan for further designing and training at their own region (for that separate project proposal will be submitted).

## Slide 8: Implementation methodology
The master craftsman of wooden-furniture-making will be selected with the help of KVIC State Office and, MDTC. Only those master-craftsman will be selected those who are making wooden-furniture at their own-home / shop.
The minimum qualification of master-craftsman will be atleast 10 pass.
MGIRI will finalized the most appropriate power tools with the help of Bharatiya Skill Development University Jaipur.
After that, MGIRI will finalize the specifications of the appropriate set of power tools (selected by a group of experts from both institutes) will be purchased through Bharatiya Skill Development University Jaipur.
Two-month experimentations on power tools for making of wooden furniture with the help of selected artisans will be organized at Bharatiya Skill Development University Jaipur.
The appropriate types of power tools will be purchased through Bharatiya Skill Development University, Jaipur after the finalization of specifications.
At the beginning of experimentation, the Bharatiya Skill Development University Jaipur will issue the power tools to the participants for practical experimental work and after successful completion of experiment these power tools will be issued on permanent basis to all successful participants.
After completing the experiment, they will be requested to start their work immediately at their home/shop. At the beginning of every quarter, they will telephonically contact to update their achievements and difficulties to the Project Coordinators of MGIRI.
MGIRI will conduct Techno-economic study of successful artisans on following parameters –
  Modernization of product after intervention
  Production rate
  Production time
  Fatigue in terms of workload and working conditions (Qualitative survey).
  Reduction in production cost
  Increase in income.
MGIRI will compose an appropriate programme and submit recommendations based on the study's outcome to KVIC.

## Slide 9: Schedule for Implementing the Project
S No | Activity | Qrt 1 | Qrt 2 | Qrt 3 | Qrt 4 | Qrt 5 | Qrt 6 | Qrt 7 | Qrt 8
1 | Identification of participants |  |  |  |  |  |  |  | 
2 | Visit to Bharatiya Skill Development University Jaipur to finalized the set of power tools |  |  |  |  |  |  |  | 
3 | Signing of MoU with Bharatiya Skill Development University Jaipur |  |  |  |  |  |  |  | 
4 | Purchase of selected set of Power Tools |  |  |  |  |  |  |  | 
5 | Experimentation with power-tools with the help of artisans at Bharatiya Skill Development University Jaipur |  |  |  |  |  |  |  | 
6 | Study of Techno-economic status of artisans. |  |  |  |  |  |  |  | 
7 | Submission of final report with appropriate recommendations for composition of new programme of Directorate of RENTI |  |  |  |  |  |  |  | 

## Slide 10: Budget Summery (For 10 Nos of participants)
Note: As per Bharatiya Skill Development University Jaipur, the participant's fee will be based on the number of participants, which will be between Rs30,000 to 50,000/-. Accordingly, the total number of participants may be increased or decreased to adjust the program within the allocated budget.
S No | Details | Rate, Rs | Quantity, Nos | Total Amount Rs
1 | Travelling Allowances (TA & DA) for the Master-craftsman equivalent to sleeper class | 6000 | 10 | 60,000
2 | Expense for two-month experimentation with artisan at BSDU, Jaipur | 40,000 | 10 | 4,00,000
3 | Food and Accommodation for artisans for two months | 11000 | 10 | 1,10,000
4 | Set of Power-tools and other essential tools finalized during experimentation | 55,000 | 10 | 5,50,000
5 | Travel of MGIRI Officers |  |  | 2,50,000
6 | Expenses for advertisements |  |  | 1,00,000
7 | Miscellaneous expenses |  |  | 30,000
 |  |  | Total | 15,00,000

## Slide 11: Expected Outcome of the Project
The following outcomes are expected from this project-
The production cost of wooden furniture will be minimized, and new contemporary designs on furniture will be visible.
The youth of the carpenter's family will come forward to take the manufacturing of wooden furniture as a career/business like pottery.
Master trainer will be available at the field level to conduct the training programs on wooden furniture manufacturing.
It will support P M Vishwakarma Yojana for selection of power tools and conducting basic and advanced training.
The requirement of tools and machines under any scheme for the carpentry artisans will be standardized.

## Slide 12: Thank you